## Sheet1
Actions | Timelines
Capstone Project Selection | 17th June'23
Project Guidance Session | 24th June’23
Doubt Clearing 1st Session | 1st/2nd July’23
Intermediate Milestone Submission | 9th July’23
Doubt Clearing Session at 2nd Session | 15th/16th July
Final Presentation & Demo | 22nd/23rd July
Final Submission | 24th Jul’23
Tasks to do: | Basic Task Board
Date | Task Info | Task Status
2023-06-27 | Git repo Creation, Infrastructure Scripts (Terraform)
VPC Creation
IAM Role and Policy Creation
Recources like DynamoDB, EC2, Lambda, AWS IOT Core, Kinesis Stream, SNS, SQS
2023-06-28 | Initial Set up
Identifying the sensors registered
Start the data flow into the Infrastructure after identifying the sensors regiestered with the company
Set the Threshold and Identify the sensors
The Data Should contain Lat Long Temparature Info Moisture Info
Design of Database
After threshold is reached we have to notify sprinkler
Each soil sensor comes under the range of a particular sprinkler. This can be directly mapped in the system.
2023-06-29 | Weather Api Sync UP
The system would also fetch air temperature and humidity readings of the farm location, from an open weather API
This can be directly sent to your computing solution, via an EC2 instance, local machine, or a Lambda function
2023-06-30 | complete the remaining part if it pending